## phase1
ID | Product Backlog Item | So that | Type | Priority | Status | Sprint
1 | As an organizer, I want to create a new event by entering its title, date, and venue. | I can add upcoming events to the system. | User story | High | Not started | Sprint 1
2 | As an organizer, I want to edit event details (e.g., date or venue) when plans change. | I can keep event information up to date. | User story | High | Not started | Sprint 1
3 | As an organizer, I want to delete an event | I can remove canceled or duplicate events from the list. | User story | High | Not started | Sprint 1
4 | As an attendee, I want to fill out a registration form for an event online. | I can register easily without manual paperwork. | User story | High | Not started | Sprint 1
5 | As an attendee, I want to view my registered events and session details. | I can track which events I’m attending | User story | Medium | Not started | sprint 2
6 | As an organizer, I want to define ticket types (VIP, Standard, Free, Early Bird) | I can offer flexible options for attendees. | User Story | High | Not started | Sprint 1
7 | As an attendee, I want to receive a QR code for my ticket after registration | I can check in quickly at the event. | User Story | High | Not started | Sprint 1
8 | As a user, I want to register using email or phone number | I can create an account with my preferred method. | User Story | High | Not started | Sprint 1
9 | As an organizer, I want to set a maximum capacity for each event | I can prevent overbooking and manage attendance limits. | User Story | Medium | Not started | Sprint 2
10 | As an organizer, I want to categorize events (conference, workshop, seminar) | I can organize and filter events more efficiently. | User Story | Medium | Not started | Sprint 2
11 | As an attendee, I want to receive reminders before my selected sessions | I don’t miss any sessions I’ve registered for. | User Story | Medium | Not started | Sprint 2
12 | As a user, I want to reset my password via email | I can regain access if I forget my login details. | User Story | Medium | Not started | Sprint 2
13 | As an organizer, I want to send notifications to followers when a new event is created | I can increase engagement and attendance. | User Story | Medium | Not started | Sprint 2
14 | As an organizer, I want to add a short description for events on the homepage | visitors can quickly understand what each event is about. | User Story | Low | Not started | Sprint 2
15 | As an organizer, I want to display event images and logos | the event page looks more attractive and professional. | User Story | Low | Not started | Sprint 2
16 | As an attendee, I want to rate the event after attending | I can share feedback to help improve future events. | User Story | Low | Not started | Sprint 2
17 | As an attendee, I want to view the number of registered participants for each event | I can gauge event popularity before joining. | User Story | Low | Not started | Sprint 2
18 | As an organizer, I want to manage the final attendee list | I can confirm attendance and prepare event logistics. | User Story | Medium | Not started | Sprint 2

## phase2
ID | Product Backlog Item | So that | Type | Priority | Status | Sprint | T-shirt Size
1 | As an organizer, I want to create a new event by entering its title, date, and venue. | I can add upcoming events to the system. | User story | High | Complete | Sprint 1 | S
2 | As an organizer, I want to edit event details (e.g., date or venue) when plans change. | I can keep event information up to date. | User story | High | Complete | Sprint 1 | S
3 | As an organizer, I want to delete an event | I can remove canceled or duplicate events from the list. | User story | High | Complete | Sprint 1 | S
4 | As an attendee, I want to fill out a registration form for an event online. | I can register easily without manual paperwork. | User story | High | Complete | Sprint 1 | M
5 | As an organizer, I want to define ticket types (VIP, Standard, Free) | I can offer flexible options for attendees. | User Story | High | Complete | Sprint 1 | S
6 | As an attendee, I want to receive a QR code for my ticket after registration | I can check in quickly at the event. | User Story | High | Complete | Sprint 1 | M
7 | As a user, I want to register using email or phone number | I can create an account with my preferred method. | User Story | High | Complete | Sprint 1 | M
8 | As an attendee, I want to view my registered events | I can track which events I’m attending | User story | Medium | Not started | sprint 2 | S
9 | As an organizer, I want to set a maximum capacity for each event | I can prevent overbooking and manage attendance limits. | User Story | Medium | On Hold | Sprint 2 | S
10 | As an organizer, I want to categorize events (conference, workshop, seminar) | I can organize and filter events more efficiently. | User Story | Medium | Not Started | Sprint 2 | S
11 | As an attendee, I want to receive reminders before my selected sessions | I don’t miss any sessions I’ve registered for. | User Story | Medium | Not Started | Sprint 2 | M
12 | As a user, I want to reset my password via email | I can regain access if I forget my login details. | User Story | Medium | Under Review | Sprint 2 | M
13 | As an organizer, I want to add a short description for events on the homepage | visitors can quickly understand what each event is about. | User Story | Low | Not Started | Sprint 2 | S
14 | As an organizer, I want to manage the final attendee list | I can confirm attendance and prepare event logistics. | User Story | Medium | In progress | Sprint 2 | M
15 | As an attendee, I want to rate both the event and the organizer after attending | I can provide fair and helpful feedback. | User Story | High | Not Started | Sprint 2 | S
16 | As an attendee, I want to suggest improvements for future events | Organizers can enhance upcoming experiences. | User Story | Medium | Not Started | Sprint 2 | S
17 | As an attendee, I want to choose when and how I receive reminders (email, SMS, or app) | I never miss an event I registered for. | User Story | Medium | Not Started | Sprint 2 | S
18 | As an attendee, I want to earn points when I attend events or give feedback | I feel rewarded for being active. | User Story | Medium | Not Started | Sprint 2 | S

## phase3
ID | Product Backlog Item | So that | Type | Priority | Status | Sprint | T-shirt Size
1 | As an attendee, I want to fill out a registration form for an event online. | I can register easily without manual paperwork. | User story | High | Complete | Sprint 1 | M
2 | As an organizer I want to set ticket capacities | I can offer flexible options for attendees. | User Story | High | Complete | Sprint 1 | M
3 | As an organizer I want to create ticket types | I can offer flexible options for attendees. | User Story | High | Complete | Sprint 1 | S
4 | As an organizer I want to delete event record | I can remove canceled or duplicate events from the list. | User story | High | Complete | Sprint 1 | S
5 | As a user I want to edit event details when needed | I can keep event information up to date. | User story | High | Complete | Sprint 1 | M
6 | As an organizer I want to add advanced event details | I can add upcoming events to the system. | User story | High | Complete | Sprint 1 | M
7 | As an organizer I want to confirm event deletion flow | I can remove canceled or duplicate events from the list. | User story | High | Complete | Sprint 1 | M
8 | As an attendee, I want to receive a QR code for my ticket after registration | I can check in quickly at the event. | User Story | High | Complete | Sprint 1 | M
9 | As a user, I want to register using email or phone number | I can create an account with my preferred method. | User Story | High | Complete | Sprint 1 | M
10 | As an organizer, I want to create a new event by entering its title, date, venue,Capacity,description) | I can add upcoming events to the system. | User story | High | Complete | Sprint 1 | S
11 | As an organizer, I want to edit event details (e.g., date or venue) when plans change. | I can keep event information up to date. | User story | High | Complete | Sprint 1 | S
12 | As an organizer, I want to delete an event | I can remove canceled or duplicate events from the list. | User story | High | Complete | Sprint 1 | S
13 | As an organizer, I want to define ticket types (VIP, Standard, Free) | I can offer flexible options for attendees. | User Story | High | Complete | Sprint 1 | S
14 | As an attendee I want to submit detailed event feedback | I can share feedback to help improve future events. | User Story | Low | Complete | Sprint 2 | M
15 | As an attendee I want to view upcoming registered events | I can gauge event popularity before joining. | User Story | Low | Complete | Sprint 2 | S
16 | As an attendee I want to view past registered events | I can gauge event popularity before joining. | User Story | Low | Complete | Sprint 2 | M
17 | As a user I want to receive event reminder | I don’t forget my upcoming events or sessions. | User Story | Medium | Complete | Sprint 2 | S
18 | As an attendee I want to submit event improvement suggestion | Organizers can enhance upcoming experiences. | User Story | Medium | Complete | Sprint 2 | S
19 | As an attendee I want to review submitted suggestions | Organizers can enhance upcoming experiences. | User Story | Medium | Complete | Sprint 2 | M
20 | As an attendee I want to track earned reward points | I feel rewarded for being active. | User Story | Medium | Complete | Sprint 2 | M
21 | As an attendee I want to select preferred notification channels | I never miss an event I registered for. | User Story | Medium | Complete | Sprint 2 | M
22 | As an organizer I want to update event summary details | visitors can quickly understand what each event is about. | User Story | Low | Complete | Sprint 2 | M
23 | As a user, I want to choose a payment method (credit card, Apple Pay, Mada) | I can pay using my preferred method. | User story | Medium | Complete | Sprint 2 | S
24 | As an organizer I want to define event capacity limits | I can prevent overbooking and manage attendance limits. | User Story | Medium | Complete | Sprint 2 | S
25 | As an organizer, I want to manage the final attendee list | I can confirm attendance and prepare event logistics. | User Story | Medium | Complete | Sprint 2 | M
26 | As an organizer I want to upload event images | the event page looks more attractive and professional. | User Story | Low | Complete | Sprint 2 | S
27 | As a user, I want to complete the payment process and receive a confirmation | I know my booking was completed successfully. | User story | Medium | Complete | Sprint 2 | M
28 | As an attendee, I want to view my registered events | I can track which events I’m attending | User story | Medium | Complete | sprint 2 | S
29 | As an organizer, I want to categorize events (conference, workshop, seminar) | I can organize and filter events more efficiently. | User Story | Medium | Complete | Sprint 2 | S
30 | As an attendee, I want to rate the event after attending | I can share feedback to help improve future events. | User Story | Low | Complete | Sprint 2 | S
31 | As an attendee, I want to view the number of registered participants for each event | I can gauge event popularity before joining. | User Story | Low | Complete | Sprint 2 | S
32 | As an attendee, I want to rate both the event and the organizer after attending | I can provide fair and helpful feedback. | User Story | High | Complete | Sprint 2 | S
33 | As an attendee, I want to suggest improvements for future events | Organizers can enhance upcoming experiences. | User Story | Medium | Complete | Sprint 2 | S
34 | As an attendee, I want to choose when and how I receive reminders (email, SMS, or app) | I never miss an event I registered for. | User Story | Medium | Complete | Sprint 2 | S
35 | As an attendee, I want to earn points when I attend events or give feedback | I feel rewarded for being active. | User Story | Medium | Complete | Sprint 2 | S