## Week1
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Rand | What did you do yesterday? | — | Clarified main backlog tasks | Identified highest‑priority items | Verified backlog prioritization | Finalized backlog structure
| What are you doing today? | Clarify the main Product Backlog tasks | Identify the highest‑priority backlog items | Verify prioritization of all backlog items | Finalize the full backlog structure | Ensure all backlog items are correctly ordered
| Is there anything blocking you? | Some items still missing details | Conflicts in ordering certain user stories | Waiting for team confirmation on two items | Missing information in two stories | Waiting for updated documentation from Lujain
Rana | What did you do yesterday? | — | Led meeting organization | Led Sprint planning | Reviewed Sprint Backlog | Validated Sprint scope
| What are you doing today? | Lead meeting organization | Lead Sprint planning activities | Review Sprint Backlog structure | Validate the Sprint scope | Ensure full team alignment before execution
| Is there anything blocking you? | Team alignment not fully clear yet | Final priorities still not confirmed | Some tasks are not linked to their user stories | Sprint Goal needs slight refinement | Conflict between two members on task order
Lujain | What did you do yesterday? | — | Documented meeting results | Documented Sprint Backlog updates | Documented final backlog version | Formatted Sprint Backlog
| What are you doing today? | Document meeting results | Document Sprint Backlog updates | Document the final version of the backlog | Format the Sprint Backlog clearly | Align documentation with the planning board
| Is there anything blocking you? | Missing clarifications from Rand | Inconsistency in how some tasks were written | Delay from Munirah on two correction items | Issues with column formatting | Conflicting versions between old and updated documents
Munirah | What did you do yesterday? | — | Assisted with backlog organization | Supported Sprint Backlog creation | Helped with corrections | Reviewed technical complexity
| What are you doing today? | Assist in organizing backlog items | Support building the Sprint Backlog | Help finalize backlog corrections | Review technical complexity of prioritized items | Confirm feasibility for Sprint execution
| Is there anything blocking you? | Dependencies not fully clarified | Two items have priority conflicts | Missing inputs from another member | Backend story requirements unclear | One story needs splitting before Sprint start
Jumanah | What did you do yesterday? | — | Supported backlog organization | Arranged Sprint Backlog items | Checked backlog accuracy | Corrected backlog errors
| What are you doing today? | Support organizing backlog items | Arrange selected items into the Sprint Backlog | Check overall backlog accuracy | Correct errors and inconsistencies | Validate the hierarchy of selected stories
| Is there anything blocking you? | Duplicate items found | Some user stories need rewriting | One story missing acceptance criteria | Missing UI details for one item | One Backend story incorrectly ordered

## Week2
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Rand | What did you do yesterday? | — | Designed upcoming events list layout. | Tested event list refresh. | Validated ordering + empty state. | Built My Registrations dashboard.
| What are you doing today? | Design upcoming events list layout with date/time labels (UI) | Verify correct loading + list refresh (Testing) | Validate correct ordering and empty-state behavior (Testing) | Build “My Registrations” dashboard listing all events (UI) | Test invalid file errors + gallery refresh (Testing)
| Is there anything blocking you? | Difficulty aligning responsive layout across screen sizes. | Inconsistent API loading time affecting refresh test. | Empty-state message not rendering correctly. | Delay fetching registered events from backend. | Some invalid file types not triggering the expected error flag.
Rana | What did you do yesterday? | — | Stored feedback in DB. | Tested past list & empty screen. | Saved notification channels. | Implemented capacity blocking.
| What are you doing today? | Store feedback linked to user & event in database (Backend) | Ensure correct past list and empty state screen (Testing) | Save chosen channels to user settings (Backend) | Block registrations when capacity is reached (Backend) | Verify remaining seats update correctly (Testing)
| Is there anything blocking you? | Missing event ID in some test payloads. | “No past events” screen failing to appear. | User preference table constraints blocking inserts. | Capacity not updating after cancellations. | Seat count not decreasing in real-time.
Lujain | What did you do yesterday? | — | Built feedback screen. | Designed reminder alert display. | Tested validation. | Added numeric-restricted capacity input.
| What are you doing today? | Build feedback screen with star rating + comment + validation (UI) | Build reminder alert display for upcoming sessions (UI) | Validate required selection + error message (Testing) | Add capacity input field with numeric restrictions (UI) | Set notification timing preferences UI (30 min / 1h / custom)
| Is there anything blocking you? | Validation loop causing double-highlight on error. | Alert component overlapping nav bar. | Validation message not triggered for null values. | Regex filter not blocking letters. | Custom-time input not activating when selected.
Munirah | What did you do yesterday? | — | Built fetch-future-events logic. | Finished reminder scheduling. | Tested multi-select accuracy. | Built attendees retrieval.
| What are you doing today? | Fetch only future events for logged-in user (Backend) | Build reminder scheduling scenario to send automatic reminders | Verify categories filter accuracy for multiple selections (Testing) | Retrieve confirmed attendees per event (Backend) | Validate count + filters + ordering (Testing)
| Is there anything blocking you? | Query returning past dates due to timezone mismatch. | Cron job not firing at scheduled test time. | Multi-select filter returning empty list on 3+ selections. | Missing JOIN with participant table. | Sort order not matching expected ascending logic.
Jumanah | What did you do yesterday? | — | Built suggestion form UI. | Saved backend suggestion. | Created editable fields. | Built attendee list UI.
| What are you doing today? | Build suggestion form with text input + category (UI) | Save suggestion with user ID + timestamp (Backend) | Create editable fields for title, description, and date (UI) | Build attendee list table with filters + search (UI) | Ensure user can rate only once per event (Testing)
| Is there anything blocking you? | Dropdown not binding selected value. | Timestamp saving in wrong timezone. | Date picker not updating bound model. | Search bar not applying filter live. | Duplicate rating allowed through API directly.

## Week3
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Rand | What did you do yesterday? | Test invalid file errors + gallery refresh (Testing) | Validate event count + filters + ordering | Validate category filter accuracy | Build star-rating widget | Create feedback API
| What are you doing today? | Validate event count + filters + ordering (Testing) | Validate category filter accuracy (Testing) | Build star-rating widget + comment validation (UI) | Create feedback API and store rating/comment correctly (Backend) | Test invalid submissions & verify saving logic (Testing)
| Is there anything blocking you? | Filters not applying when switching categories. | Multi-select categories causing empty results. | Comment box not resetting after submission. | Feedback endpoint returning 400 for missing header. | Invalid values bypassing validation in one scenario.
Rana | What did you do yesterday? | Verify remaining seats update correctly | Validate correct category filtering logic | Retrieve and update participant count | Verify success message accuracy | Check category correctness
| What are you doing today? | Validate correct category filtering logic (Testing) | Retrieve and update participant count dynamically (Backend) | Verify success message + booking record accuracy (Testing) | Check category shows correctly + matches filters (Testing) | Validate reminders follow method/time (Testing)
| Is there anything blocking you? | Category “Workshops” not matching filter rules. | Participant count not syncing after refresh. | Booking ID not appearing on success screen. | Category label misaligned in event card. | Email reminder delayed by over 5 minutes.
Lujain | What did you do yesterday? | Set notification timing preferences UI | Create suggestion review list UI | Test points increase logic | Save summary updates | Implement multi-image uploader
| What are you doing today? | Create suggestion review list with filters (UI) | Test points increase logic after each action (Testing) | Save summary updates to event table (Backend) | Implement multi-image uploader (Backend duplicate validation) | Validate upload rules match event format (UI)
| Is there anything blocking you? | Filter dropdown not loading categories. | Points not incrementing after rating submission. | Summary field overwriting previous entries. | Duplicate detection not stable with fast uploads. | Wrong error message shown for invalid file types.
Munirah | What did you do yesterday? | Validate count + filters + ordering | Validate error flow | Verified user rating list | Validate scroll + refresh | Save suggestion attachments
| What are you doing today? | Validate error flow + empty state (Testing) | Verify user appears correctly in every rating list (Testing) | Validate scroll + refresh logic for “My Registrations” | Save suggestion with attachments securely (Backend) | Test update of points table after feedback (Testing)
| Is there anything blocking you? | Empty state message overlapping filter bar. | Missing user in organizer rating list. | Refresh pulls duplicate items occasionally. | Attachment size validation failing. | Points table not updating after comment submission.
Jumanah | What did you do yesterday? | Ensure user can rate only once per event | Verified booking workflow | Create confirmation screen UI | Validate sorting | Store points after attendance update
| What are you doing today? | Verify booking workflow end-to-end (Testing) | Create confirmation screen UI after event completion | Validate category match & sort order (Testing) | Store points after attendance or feedback submission (Backend) | Validate all rating counts per event (Testing)
| Is there anything blocking you? | Payment simulation not updating booking status. | Confirmation text misaligned on small screens. | Incorrect sort order when mixing past + upcoming. | Points update endpoint returning null. | Rating count mismatch between event and organizer views.

## Week4
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Rand | What did you do yesterday? | Yesterday: Test invalid submissions & verify saving logic | Yesterday: Confirm updated capacity logic | Yesterday: Built payment summary screen | Yesterday: Validated UI consistency | Yesterday: Tested rating limits
| What are you doing today? | Today: Confirm updated capacity when seats are filled (Testing) | Today: Build summary screen for simulated payment result (UI) | Today: Maintain UI consistency for all event lists (Testing) | Today: Test rating limits & ensure only one submission (Testing) | Today: Validate correct ordering of rating panel (Testing)
| Is there anything blocking you? | Impediments: Capacity not decreasing after multiple test bookings. | Impediments: Summary screen not rendering payment status correctly. | Impediments: Inconsistent spacing in event cards. | Impediments: System allows new rating through quick double-click. | Impediments: Rating panel appearing at bottom instead of top.
Rana | What did you do yesterday? | Yesterday: Validate reminders follow method/time | Yesterday: Validate ordering & empty behavior | Yesterday: Validate image refresh | Yesterday: Applied capacity rules | Yesterday: Updated payment method
| What are you doing today? | Today: Validate correct ordering and empty-state behavior (Testing) | Today: Validate gallery refresh and invalid image error handling | Today: Apply capacity rule to block excess registrations (Backend) | Today: Save selected method before payment simulation (UI) | Today: Fetch any future events for logged-in user (Backend)
| Is there anything blocking you? | Impediments: Empty-state not showing on Android devices. | Impediments: Image refresh lagging after deletion. | Impediments: Capacity check firing too late. | Impediments: Selected method not binding to form. | Impediments: Incorrect filtering showing past events too.
Lujain | What did you do yesterday? | Yesterday: Validate upload rules | Yesterday: Built attendee list UI | Yesterday: Tested attendee list matching | Yesterday: Built category filter UI | Yesterday: Tested badge logic
| What are you doing today? | Today: Build attendee list table with filters + search (UI) | Today: Test validation + full list matching (Testing) | Today: Create category filter UI with multi-select options (UI) | Today: Implement badge logic for “Top Rated / Most Active” (Testing) | Today: Update badge after review submission (Backend)
| Is there anything blocking you? | Impediments: Search bar not narrowing results correctly. | Impediments: Table columns misaligned after filtering. | Impediments: Multi-select chip not removable. | Impediments: Badge not updating after submitting review. | Impediments: Badge API returning outdated scores.
Munirah | What did you do yesterday? | Yesterday: Test update of points table | Yesterday: Validated event panel sorting | Yesterday: Validated participant increments | Yesterday: Implemented suggestion inbox | Yesterday: Saved suggestion attachments
| What are you doing today? | Today: Validate sorting logic for event panel (Testing) | Today: Validate participant counter increments (Testing) | Today: Implement suggestion inbox list (UI) | Today: Save suggestion with attachments securely (Backend) | Today: Validate scroll and load logic for events (Testing)
| Is there anything blocking you? | Impediments: Sorting results inconsistent across browsers. | Impediments: Counter not updating when removing a participant. | Impediments: Suggestion items overlapping timestamps. | Impediments: File path not saving in DB. | Impediments: Infinite scroll stuck on loading spinner.
Jumanah | What did you do yesterday? | Yesterday: Validate all rating counts per event | Yesterday: Built notification preference UI | Yesterday: Tested data flow | Yesterday: Implemented multi-image uploader | Yesterday: Validated category sorting
| What are you doing today? | Today: Create notification preferences (Email/SMS/In-App + timing) (UI) | Today: Test data flow and validation for all modules assigned (Testing) | Today: Build multi-image uploader area with preview thumbnails (Backend) | Today: Validate category match & sort order (Testing) | Today: Update dashboard charts (UI)
| Is there anything blocking you? | Impediments: Toggle not saving user preference. | Impediments: Notification settings not updating in real time. | Impediments: Preview list not updating after deletion. | Impediments: Category filtering incorrect for newly added events. | Impediments: Chart values not refreshing after data reload.

## Week5
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Rand | What did you do yesterday? | Yesterday: Validate correct ordering of rating panel (Testing) | Yesterday: Verify remaining seats update correctly | Yesterday: Validate correct count + filters | Yesterday: Validate expandable filters | Yesterday: Validate reminder method/time
| What are you doing today? | Today: Verify remaining seats update correctly (Testing) | Today: Validate correct count + filters + ordering (Testing) | Today: Validate expandable filters with join/cancel behavior (Testing) | Today: Validate reminder follow method/time (Testing) | Today: Test invalid submissions and verify saving logic (Testing)
| Is there anything blocking you? | Impediments: Seat count not updating after cancellation. | Impediments: Filters not resetting after clearing selections. | Impediments: Expandable panel not collapsing after join action. | Impediments: SMS reminder not sending during testing cycle. | Impediments: Invalid feedback still accepted when comment empty.
Rana | What did you do yesterday? | Yesterday: Fetch any future events for logged-in user (Backend) | Yesterday: Validate category filtering logic | Yesterday: Updated participant count | Yesterday: Validate image handling | Yesterday: Saved payment method selection
| What are you doing today? | Today: Validate correct category filtering logic (Testing) | Today: Retrieve and update participant count dynamically (Backend) | Today: Validate gallery refresh and invalid image error handling | Today: Save selected method before payment simulation (UI) | Today: Validate reminders follow method/time (Testing)
| Is there anything blocking you? | Impediments: Category “Seminar” not returning matches. | Impediments: Participant count stuck at previous value after refresh. | Impediments: Invalid image types not triggering alert. | Impediments: Selected option resets when navigating back. | Impediments: Reminder interval mismatch with saved preference.
Lujain | What did you do yesterday? | Yesterday: Update badge after review submission | Yesterday: Test points increase | Yesterday: Saved summary updates | Yesterday: Set event capacity | Yesterday: Validate capacity update
| What are you doing today? | Today: Test points increase logic after each action (Testing) | Today: Save summary updates to event table (Backend) | Today: Set maximum capacity for each event (UI) | Today: Validate correct capacity update (Testing) | Today: Store ratings updated correctly (Testing)
| Is there anything blocking you? | Impediments: Points not increasing after organizer-rating. | Impediments: Summary overwriting existing event description. | Impediments: Capacity field not maintaining value after reload. | Impediments: Max capacity still exceeded in rare case. | Impediments: Ratings not syncing across event detail view.
Munirah | What did you do yesterday? | Yesterday: Validate scroll and load logic for events | Yesterday: Validate error flow | Yesterday: Validate participant increments | Yesterday: Verified user rating list | Yesterday: Validate rendering
| What are you doing today? | Today: Validate error flow + empty state (Testing) | Today: Validate participant counter increments (Testing) | Today: Verify user appears correctly in every rating list (Testing) | Today: Validate rendering with multiple images selected (Testing) | Today: Validate correct ordering of attendees (Testing)
| Is there anything blocking you? | Impediments: Error message displayed with wrong icon. | Impediments: Participant counter duplicate increment. | Impediments: User missing in organizer-rating tab. | Impediments: Multi-image preview overlapping grid. | Impediments: Wrong ordering when two attendees have same timestamp.
Jumanah | What did you do yesterday? | Yesterday: Update dashboard charts (UI) | Yesterday: Validate suggestion filters | Yesterday: Stored categories correctly | Yesterday: Created editable rating UI | Yesterday: Verified full data flow
| What are you doing today? | Today: Validate suggestion loading & filters (Testing) | Today: Store category chosen per event (Backend) | Today: Create editable form for rating sections (UI) | Today: Validate data flow and validation for all modules (Testing) | Today: Verify attachments & uploads saved correctly (Backend)
| Is there anything blocking you? | Impediments: Filter tab not updating active state. | Impediments: Category not stored when event updated twice. | Impediments: Organizer-rating field not saving UI changes. | Impediments: Data inconsistency in attendee records. | Impediments: Some attachments stored with wrong path.

## Week6
Team member | Question | Sunday | Monday | Tuesday | Wednesday | Thursday
Rand | What did you do yesterday? | Yesterday: Test invalid submissions and verify saving logic | Yesterday: Verified comment handling | Yesterday: Built instant category filtering | Yesterday: Built registration dashboard | Yesterday: Tested invalid feedback
| What are you doing today? | Today: Verify empty comment handling + correct rating storage (Testing) | Today: Filter event list by category with instant refresh (UI) | Today: Build “My Registrations” dashboard listing all events (UI) | Today: Test invalid submissions and verify feedback saved correctly (Testing) | Today: Validate correct ordering of rating panel (Testing)
| Is there anything blocking you? | Impediments: System still accepts spaces-only comment. | Impediments: UI flickers on fast category switching. | Impediments: Some events missing from dashboard on first load. | Impediments: Duplicate feedback detected on fast double-tap. | Impediments: Rating panel not updating after new submission.
Rana | What did you do yesterday? | Yesterday: Validate reminders follow method/time | Yesterday: Validated booking success | Yesterday: Retrieved confirmed attendees | Yesterday: Validated participant count | Yesterday: Fetched old attended events
| What are you doing today? | Today: Validate success message + booking record accuracy (Testing) | Today: Retrieve confirmed attendees per event (Backend) | Today: Validate correct participant count and ordering (Testing) | Today: Fetch attended events older than current date (Backend) | Today: Ensure correct past list and empty state screen (Testing)
| Is there anything blocking you? | Impediments: Success pop-up not closing automatically. | Impediments: Missing attendees when event has >15 users. | Impediments: Sorting by registration time not consistent. | Impediments: Query retrieving future events mistakenly. | Impediments: Empty state message clipped on mobile.
Lujain | What did you do yesterday? | Yesterday: Store ratings updated correctly | Yesterday: Built multi-select category UI | Yesterday: Validated selection error | Yesterday: Added capacity restriction | Yesterday: Implemented reminder logic
| What are you doing today? | Today: Create category filter UI with multi-select options (UI) | Today: Validate required selection + error message (Testing) | Today: Add numeric restrictions to capacity input (UI) | Today: Implement reminder sending logic (email/notification) (Backend) | Today: Test points increase logic after each action (Testing)
| Is there anything blocking you? | Impediments: Chips overlapping when selecting many items. | Impediments: Invalid selection still passes without warning. | Impediments: Input still allows symbols on mobile keyboard. | Impediments: Email reminders not hitting test inbox. | Impediments: Points table not updating after review submission.
Munirah | What did you do yesterday? | Yesterday: Validate correct ordering of attendees | Yesterday: Validated empty-state | Yesterday: Validated category sorting | Yesterday: Verified registration scroll | Yesterday: Validated attendance points
| What are you doing today? | Today: Validate correct ordering and empty-state behavior (Testing) | Today: Validate category match & sort order (Testing) | Today: Validate scroll + refresh logic for “My Registrations” (Testing) | Today: Validate points update after attendance (Testing) | Today: Validate rendering with multiple images selected (Testing)
| Is there anything blocking you? | Impediments: Wrong “no attendees yet” state triggered. | Impediments: Sort breaks when two events share same date. | Impediments: Extra scroll appended after refresh. | Impediments: Some events not giving points after check-in. | Impediments: Last image thumbnail not showing.
Jumanah | What did you do yesterday? | Yesterday: Verify attachments & uploads saved correctly | Yesterday: Created editable rating UI | Yesterday: Validated full data flow | Yesterday: Stored categories | Yesterday: Validated suggestion filters
| What are you doing today? | Today: Create editable form for rating sections (UI) | Today: Validate data flow and validation for all modules (Testing) | Today: Store category chosen per event (Backend) | Today: Validate suggestion loading & filters (Testing) | Today: Update dashboard charts (UI)
| Is there anything blocking you? | Impediments: Rating fields not applying changes instantly. | Impediments: Data mismatch between ratings & event. | Impediments: Backend saves wrong category ID in rare cases. | Impediments: Filter not applying when switching tabs quickly. | Impediments: Chart labels overlapping after refresh.