## Phas1
Task # | User Story | Task Description | Assigned To | Effort | Priority | Status
1 | User Story (1) | Design UI | Lujain | 3 pts | High | Not Started
2 | User Story (1) | Implement backend logic | Rand | 5 pts | High | Not Started
3 | User Story (1) | Test end-to-end functionality | Munirah | 2 pts | High | Not Started
4 | User Story (2) | Design UI | Jumanah | 3 pts | High | Not Started
5 | User Story (2) | Implement backend logic | Rana | 5 pts | High | Not Started
6 | User Story (2) | Test end-to-end functionality | Lujain | 2 pts | High | Not Started
7 | User Story (3) | Design UI | Rand | 3 pts | High | Not Started
8 | User Story (3) | Implement backend logic | Munirah | 5 pts | High | Not Started
9 | User Story (3) | Test end-to-end functionality | Jumanah | 2 pts | High | Not Started
10 | User Story (4) | Design UI | Rana | 3 pts | High | Not Started
11 | User Story (4) | Implement backend logic | Lujain | 5 pts | High | Not Started
12 | User Story (4) | Test end-to-end functionality | Rand | 2 pts | High | Not Started
13 | User Story (6) | Design UI | Munirah | 3 pts | High | Not Started
14 | User Story (6) | Implement backend logic | Jumanah | 5 pts | High | Not Started
15 | User Story (6) | Test end-to-end functionality | Rana | 2 pts | High | Not Started
16 | User Story (7) | Design UI | Lujain | 3 pts | High | Not Started
17 | User Story (7) | Implement backend logic | Rand | 5 pts | High | Not Started
18 | User Story (7) | Test end-to-end functionality | Munirah | 2 pts | High | Not Started
19 | User Story (8) | Design UI | Jumanah | 3 pts | High | Not Started
20 | User Story (8) | Implement backend logic | Rana | 5 pts | High | Not Started
21 | User Story (8) | Test end-to-end functionality | Lujain | 2 pts | High | Not Started

## Phase2
Task# | User Story | Task Description | Assigned To | Effort | Priority | Status
1 | User Registration | Design registration UI | Rand | 3 pts | High | Done
2 | User Registration | Develop registration backend API | Munirah | 5 pts | High | Done
3 | User Registration | Implement validation & error handling | Jumanah | 3 pts | High | Done
4 | User Registration | Test registration flow | Rana | 2 pts | High | Done
5 | Event Creation and Management | Design event creation UI | Lujain | 3 pts | High | Done
6 | Event Creation and Management | Create event database schema | Munirah | 4 pts | High | Done
7 | Event Creation and Management | Develop CRUD APIs for events | Rand | 5 pts | High | Done
8 | Event Creation and Management | Test event management module | Rana | 2 pts | High | Done
9 | Ticket Management | Design ticket form UI | Lujain | 2 pts | Medium | Done
10 | Ticket Management | Implement ticket type logic | Munirah | 4 pts | Medium | Done
11 | Ticket Management | Connect tickets to event capacity | Jumanah | 3 pts | Medium | Done
12 | Ticket Management | Integration testing | Rand | 2 pts | Medium | Done
13 | QR Code Check-in | Generate unique QR codes | Lujain | 3 pts | Medium | Done
14 | QR Code Check-in | Integrate QR code scanning feature | Jumanah | 4 pts | Medium | Done
15 | QR Code Check-in | Test QR code functionality | Rana | 2 pts | Medium | Done
16 | Create New Event | Develop form and backend for event creation | Lujain | 3 pts | High | Done
17 | Edit Event Details | Implement edit event functionality | Munirah | 3 pts | High | Done
18 | Delete Event | Add delete feature for event management | Rana | 2 pts | Medium | Done
19 | Create Ticket Types | Allow organizers to define ticket categories (VIP, Regular, Free) | Rand | 3 pts | High | Done
20 | Set Ticket Capacity | Implement capacity limits per ticket type | Jumanah | 3 pts | Medium | Done
21 | Auto Update Ticket Availability | Automatically update available tickets when attendees register | Lujain | 2 pts | Medium | Done

## Phase3
Task# | User Story | Task Description | Assigned To | Effort | Priority | Status
1 | User Story (14) | Build feedback screen with star rating + comment field + validation (UI) | Lujain | 3 pts | High | Complete
2 | User Story (14) | Save feedback linked to user & event in database (Backend) | Rana | 5 pts | High | Complete
3 | User Story (14) | Verify empty comment handling + correct rating storage (Testing) | Rand | 2 pts | High | Complete
4 | User Story (15) | Design upcoming events list layout with date/time labels (UI) | Jumanah | 3 pts | High | Complete
5 | User Story (15) | Fetch only future events for logged-in user (Backend) | Munirah | 5 pts | High | Complete
6 | User Story (15) | Test filtering accuracy + sorting by date (Testing) | Lujain | 2 pts | High | Complete
7 | User Story (16) | Create past events history cards with event summary (UI) | Rana | 3 pts | High | Complete
8 | User Story (16) | Load attended events older than current date (Backend) | Rand | 5 pts | High | Complete
9 | User Story (16) | Ensure correct past list and empty state screen (Testing) | Jumanah | 2 pts | High | Complete
10 | User Story (17) | Build reminder alert display for upcoming sessions (UI) | Munirah | 3 pts | High | Complete
11 | User Story (17) | Implement reminder sending logic (email/notification) (Backend) | Lujain | 5 pts | High | Complete
12 | User Story (17) | Validate reminder triggers at correct timing (Testing) | Rana | 2 pts | High | Complete
13 | User Story (18) | Build suggestion form with text input + category (UI) | Rand | 3 pts | Medium | Complete
14 | User Story (18) | Save suggestion with user ID + timestamp (Backend) | Jumanah | 5 pts | Medium | Complete
15 | User Story (18) | Test validation & successful submission (Testing) | Munirah | 2 pts | Medium | Complete
16 | User Story (19) | Create suggestion review list with filters (UI) | Lujain | 3 pts | Medium | Complete
17 | User Story (19) | Fetch all submitted suggestions with pagination (Backend) | Rana | 5 pts | Medium | Complete
18 | User Story (19) | Validate correct loading and list refresh (Testing) | Rand | 2 pts | Medium | Complete
19 | User Story (20) | Show points dashboard with progress bar (UI) | Jumanah | 3 pts | Medium | Complete
20 | User Story (20) | Update points upon attendance or feedback (Backend) | Munirah | 5 pts | Medium | Complete
21 | User Story (20) | Test points increase logic after each action (Testing) | Lujain | 2 pts | Medium | Complete
22 | User Story (21) | Create channel selector (Push / Email / SMS) (UI) | Rana | 3 pts | Medium | Complete
23 | User Story (21) | Save chosen channels to user settings (Backend) | Rand | 5 pts | Medium | Complete
24 | User Story (21) | Ensure notifications sent only to selected channels (Testing) | Jumanah | 2 pts | Medium | Complete
25 | User Story (22) | Create editable fields for title, description, and date (UI) | Munirah | 3 pts | Medium | Complete
26 | User Story (22) | Save summary updates to event table (Backend) | Lujain | 5 pts | Medium | Complete
27 | User Story (22) | Verify updates appear instantly across screens (Testing) | Rana | 2 pts | Medium | Complete
28 | User Story (23) | Create payment method selector (Mada, Apple Pay, Visa) (UI) | Rand | 3 pts | High | Complete
29 | User Story (23) | Save selected method before confirming payment (Backend) | Jumanah | 5 pts | High | Complete
30 | User Story (23) | Validate required selection + error message (Testing) | Munirah | 2 pts | High | Complete
31 | User Story (24) | Add capacity input field with numeric restrictions (UI) | Lujain | 3 pts | Medium | Complete
32 | User Story (24) | Block registrations when capacity is reached (Backend) | Rana | 5 pts | Medium | Complete
33 | User Story (24) | Verify remaining seats update correctly (Testing) | Rand | 2 pts | Medium | Complete
34 | User Story (25) | Build attendee list table with filters + search (UI) | Jumanah | 3 pts | Medium | Complete
35 | User Story (25) | Retrieve confirmed attendees per event (Backend) | Munirah | 5 pts | Medium | Complete
36 | User Story (25) | Check list accuracy + sorting (Testing) | Lujain | 2 pts | Medium | Complete
37 | User Story (26) | Build multi-image upload area with preview thumbnails (UI) | Rana | 3 pts | Low | Complete
38 | User Story (26) | Validate file size/type + store images securely (Backend) | Rand | 5 pts | Low | Complete
39 | User Story (26) | Test invalid file errors + gallery refresh (Testing) | Jumanah | 2 pts | Low | Complete
40 | User Story (27) | Create payment confirmation screen with transaction summary (UI) | Munirah | 3 pts | High | Complete
41 | User Story (27) | Simulate payment API + update booking status (Backend) | Lujain | 5 pts | High | Complete
42 | User Story (27) | Verify success message + booking record accuracy (Testing) | Rana | 2 pts | High | Complete
43 | User Story (28) | Build “My Registrations” dashboard listing all events (UI) | Rand | 3 pts | High | Complete
44 | User Story (28) | Load all registrations linked to user ID (Backend) | Jumanah | 5 pts | High | Complete
45 | User Story (28) | Validate event count + filters + ordering (Testing) | Munirah | 2 pts | High | Complete
46 | User Story (29) | Add category dropdown in event form (UI) | Lujain | 3 pts | Medium | Complete
47 | User Story (29) | Save selected category for each event (Backend) | Rana | 5 pts | Medium | Complete
48 | User Story (29) | Check category shows correctly + matches filters (Testing) | Rand | 2 pts | Medium | Complete
49 | User Story (30) | Build rating panel shown after event completion (UI) | Jumanah | 3 pts | Medium | Complete
50 | User Story (30) | Store rating linked to attendance record (Backend) | Munirah | 5 pts | Medium | Complete
51 | User Story (30) | Ensure user can rate only once per event (Testing) | Lujain | 2 pts | Medium | Complete
52 | User Story (31) | Add participants counter next to event card (UI) | Rana | 3 pts | High | Complete
53 | User Story (31) | Retrieve and update participant count dynamically (Backend) | Rand | 5 pts | High | Complete
54 | User Story (31) | Validate counter changes with join/cancel (Testing) | Jumanah | 2 pts | High | Complete
55 | User Story (32) | Create two rating sections (event + organizer) (UI) | Munirah | 3 pts | Low | Complete
56 | User Story (32) | Save both ratings in separate tables (Backend) | Lujain | 5 pts | Low | Complete
57 | User Story (32) | Verify averages calculated correctly (Testing) | Rana | 2 pts | Low | Complete
58 | User Story (33) | Build suggestion form with optional attachment (UI) | Rand | 3 pts | Low | Complete
59 | User Story (33) | Store suggestions + attachments securely (Backend) | Jumanah | 5 pts | Low | Complete
60 | User Story (33) | Test validation + file upload edge cases (Testing) | Munirah | 2 pts | Low | Complete
61 | User Story (34) | Create reminder preferences (Email/SMS/In-App + timing) (UI) | Lujain | 3 pts | Low | Complete
62 | User Story (34) | Save chosen channels + timing (Backend) | Rana | 5 pts | Low | Complete
63 | User Story (34) | Validate reminders follow method/time (Testing) | Rand | 2 pts | Low | Complete
64 | User Story (35) | Show 'Points earned' toast after actions (UI) | Jumanah | 3 pts | Low | Complete
65 | User Story (35) | Update points table after attendance or feedback submission. (Backend) | Munirah | 5 pts | Low | Complete
66 | User Story (35) | Verify points totals after multiple actions and scenarios.(Testing) | Lujain | 2 pts | Low | Complete